ASSIGNMENT 2

Software Project Management (SPM)

Smart Co-Working Space Booking & Management System

| Student Name | Muhammad Amir |
| --- | --- |
| SAP ID | 55662 |
| Section | BSSE 6 |
| Subject | Software Project Management (SPM) |
| Group No | Group 6 |
| Role | Team Leader / Project Manager / Technical Analyst |
| Submission Date | 2025 |

# 1. Resource Planning

## 1.1 Human Resources

| Name | Role | Duration | Responsibilities |
| --- | --- | --- | --- |
| Muhammad Amir | Project Manager / Full-Stack Dev / Analyst | 4 months | Planning, development, documentation, testing, deployment |

## 1.2 Hardware Resources

| Hardware | Specification | Purpose |
| --- | --- | --- |
| Development Laptop | Intel Core i5, 8GB RAM, 256GB SSD | Development & Testing |
| Cloud Server (AWS EC2) | 2 vCPU, 4GB RAM, 80GB SSD | Production Hosting |
| Test Devices | Android/iOS phones + various browsers | Cross-device Testing |

## 1.3 Software Resources

| Software | Version / Type | Purpose |
| --- | --- | --- |
| VS Code | Latest (Free) | Code Development IDE |
| Node.js / React.js | LTS versions (Free) | Backend & Frontend Development |
| MySQL Workbench | 8.0 (Free) | Database Design & Management |
| Postman | Latest (Free) | API Testing |
| GitHub | Free Tier | Version Control & Collaboration |
| Figma | Free Tier | UI/UX Wireframing |
| AWS Console | Cloud (Paid) | Deployment & Hosting |

## 1.4 Financial Resources

Total project budget is estimated at PKR 198,000 covering developer salary, cloud hosting, domain/SSL, software licences, testing activities, and a 10% contingency reserve. The breakdown is detailed in Section 3 (Cost Planning).

# 2. Time Planning

## 2.1 Activity List with Dependencies

| # | Activity | Dependency | Timeline | Duration | Resource |
| --- | --- | --- | --- | --- | --- |
| 1 | Project Kickoff & Planning | None | 06 Jan – 12 Jan 2025 | 1 week | Amir (PM) |
| 2 | Requirements Gathering & Analysis | Task 1 | 06 Jan – 19 Jan 2025 | 2 weeks | Amir (Analyst) |
| 3 | System Architecture Design | Task 2 | 20 Jan – 02 Feb 2025 | 2 weeks | Amir (Architect) |
| 4 | Database Design | Task 3 | 27 Jan – 09 Feb 2025 | 1 week | Amir (Dev) |
| 5 | UI/UX Wireframing & Prototyping | Task 3 | 27 Jan – 09 Feb 2025 | 2 weeks | Amir (Dev) |
| 6 | Backend API Development | Task 4 | 10 Feb – 09 Mar 2025 | 4 weeks | Amir (Dev) |
| 7 | Frontend Development | Task 5, 6 | 17 Feb – 16 Mar 2025 | 4 weeks | Amir (Dev) |
| 8 | Payment Gateway Integration | Task 6 | 10 Mar – 23 Mar 2025 | 1 week | Amir (Dev) |
| 9 | System Integration & Unit Testing | Task 7, 8 | 17 Mar – 30 Mar 2025 | 2 weeks | Amir (Tester) |
| 10 | User Acceptance Testing (UAT) | Task 9 | 31 Mar – 06 Apr 2025 | 1 week | Amir + Client |
| 11 | Bug Fixes & Revisions | Task 10 | 07 Apr – 13 Apr 2025 | 1 week | Amir (Dev) |
| 12 | Deployment & Production Setup | Task 11 | 14 Apr – 20 Apr 2025 | 1 week | Amir (DevOps) |
| 13 | Training & Handover | Task 12 | 21 Apr – 27 Apr 2025 | 1 week | Amir (PM) |
| TOTAL PROJECT DURATION |  |  |  | 16 Weeks |  |

## 2.2 Gantt Chart

A detailed Gantt chart has been prepared in Microsoft Excel (separate file: Gantt_Chart_SPM_Amir.xlsx). It illustrates the full 16-week project timeline from 06 January 2025 to 27 April 2025, colour-coded by phase, with task bars, week columns, and a legend.

| Phase | Colour & Tasks Covered |
| --- | --- |
| Phase 1 – Initiation (Green) | Kickoff, Requirements Gathering & Analysis (Weeks 1–2) |
| Phase 2 – Design (Blue) | System Architecture, Database Design, UI/UX Wireframing (Weeks 3–5) |
| Phase 3 – Development (Orange) | Backend API, Frontend, Payment Gateway Integration (Weeks 6–10) |
| Phase 4 – Testing (Purple) | Unit Testing, UAT, Bug Fixes (Weeks 11–14) |
| Phase 5 – Deployment (Red) | Production Deployment, Training & Handover (Weeks 15–16) |

# 3. Cost Planning

## 3.1 Detailed Cost Estimation

| # | Cost Category | Unit Cost | Qty | Duration | Total (PKR) |
| --- | --- | --- | --- | --- | --- |
| 1 | Developer Salary (Muhammad Amir) | PKR 30,000 | 1 person | 4 months | PKR 120,000 |
| 2 | Cloud Hosting (AWS EC2) | PKR 5,000 | 1 server | 4 months | PKR 20,000 |
| 3 | Domain Registration | PKR 2,500 | 1 domain | 1 year | PKR 2,500 |
| 4 | SSL Certificate | PKR 2,500 | 1 | 1 year | PKR 2,500 |
| 5 | Software Tools & Licences | PKR 10,000 | Lump sum | One-time | PKR 10,000 |
| 6 | Payment Gateway Setup (Stripe) | PKR 5,000 | 1 | One-time | PKR 5,000 |
| 7 | Testing & QA Activities | PKR 15,000 | Lump sum | One-time | PKR 15,000 |
| 8 | Documentation & Training Material | PKR 5,000 | Lump sum | One-time | PKR 5,000 |
| 9 | Contingency Reserve (10%) | – | – | – | PKR 18,000 |
| TOTAL PROJECT BUDGET |  |  |  |  | PKR 198,000 |

## 3.2 Budget Summary Sheet

| Costs | Expected Benefits |
| --- | --- |
| Total Development Cost: PKR 198,000 | Reduce staff manual work → Save PKR 15,000/month |
| Ongoing Hosting: PKR 5,000/month | 25–35% increased workspace utilisation |
| Maintenance: PKR 5,000/month (estimated) | Reduced booking errors → fewer client complaints |
| Annual Operational Cost: ~PKR 120,000 | Scalable to multiple locations without added staff |
|  | Estimated Net Annual Benefit: PKR 250,000+ |

Break-Even Point: The system is expected to recover its development cost within approximately 8–10 months of operation.

# 4. Risk Planning

## 4.1 Risk Register

| ID | Risk Description | Category | Prob. | Impact | Rating | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- | --- |
| R1 | Requirement changes from client mid-project | Scope | Medium | High | HIGH | Freeze requirements after sign-off; use formal change request process |
| R2 | Single developer unavailability (health/emergency) | Resource | Low | Critical | HIGH | Daily code commits; keep all documentation up to date; maintain backups |
| R3 | Schedule delays due to technical complexity | Schedule | Medium | High | HIGH | 2-week buffer built in; tasks broken into daily milestones |
| R4 | Payment gateway integration failure | Technical | Low | High | MEDIUM | Use well-documented Stripe API; test in sandbox environment early |
| R5 | Data loss or security breach | Security | Low | Critical | MEDIUM | Regular DB backups; JWT authentication; HTTPS enforced |
| R6 | Budget overrun | Financial | Low | Medium | LOW | 10% contingency reserve allocated; weekly expense monitoring |
| R7 | Low user adoption by staff or clients | Operational | Medium | Medium | MEDIUM | Conduct training sessions; design intuitive UI/UX; gather feedback |
| R8 | Cloud service downtime | Infrastructure | Low | High | MEDIUM | AWS SLA 99.9% uptime; implement error handling & monitoring |

## 4.2 Risk Priority Matrix

| Probability / Impact | Low Impact | Medium Impact | High Impact | Critical Impact |
| --- | --- | --- | --- | --- |
| High Probability | Medium | HIGH | HIGH | CRITICAL |
| Medium Probability | Low | MEDIUM | HIGH (R1,R3,R7) | HIGH |
| Low Probability | Low (R6) | MEDIUM (R4,R5,R8) | MEDIUM | HIGH (R2) |

# 5. Quality Planning

## 5.1 Quality Standards & Objectives

The quality plan ensures the system meets defined functional and non-functional requirements before delivery. The following standards apply throughout the project lifecycle:

- ISO/IEC 25010 – Software Quality Model (functionality, reliability, security, usability, maintainability).

- All API endpoints must be documented and tested in Postman before integration.

- Code must follow standardised naming conventions and be reviewed against ESLint rules.

- All user-facing features must be validated through unit, integration, and UAT testing.

- Security testing must confirm HTTPS enforcement, JWT token validation, and SQL injection prevention.

## 5.2 Quality Metrics & Standards

| ID | Quality Standard | Metric / Target | Frequency | Measurement Method |
| --- | --- | --- | --- | --- |
| QS-01 | All functional modules operational | 100% test cases passed | Per sprint | Automated + manual testing |
| QS-02 | System response time | < 3 seconds for core transactions | Load testing | Performance/load testing tool |
| QS-03 | Defect density | < 5 bugs per module | Per sprint | Bug tracking (GitHub Issues) |
| QS-04 | Code quality | No critical code smells | Weekly | ESLint / SonarQube review |
| QS-05 | Security compliance | HTTPS + JWT + input validation active | Pre-deployment | Security audit checklist |
| QS-06 | UAT satisfaction | >= 4/5 rating | Post-UAT | Client feedback forms |
| QS-07 | System uptime | >= 99% post-deployment | Daily | AWS CloudWatch monitoring |

## 5.3 Quality Assurance Activities

| Activity | Description | Timing | Owner |
| --- | --- | --- | --- |
| Code Reviews | Review backend and frontend code for correctness, standards, and security. | After each development sprint | Amir (Dev) |
| Unit Testing | Test individual functions/modules in isolation using test scripts. | During development | Amir (Tester) |
| Integration Testing | Test API endpoints and frontend-backend data flow. | After backend completion | Amir (Tester) |
| Security Testing | Verify HTTPS, authentication, input sanitisation, and SQL injection prevention. | Pre-UAT | Amir (Tester) |
| Performance/Load Testing | Simulate 50 concurrent users; verify sub-3s response times. | Pre-deployment | Amir (DevOps) |
| User Acceptance Testing | Validate system with real users; collect structured feedback. | Week 13 | Amir + Client |
| Post-deployment Monitoring | Monitor system uptime, errors, and performance via AWS CloudWatch. | Post-launch | Amir (DevOps) |

# 6. Monitoring & Control Planning

## 6.1 Key Performance Indicators (KPIs)

| # | KPI | Measurement Method | Target | Frequency |
| --- | --- | --- | --- | --- |
| 1 | Schedule Variance (SV) | Planned vs Actual completion | <= 0 (on schedule) | Weekly |
| 2 | Cost Variance (CV) | Planned vs Actual spend | <= 0 (on budget) | Bi-weekly |
| 3 | Defect Density | Bugs per module in testing | < 5 bugs per module | Per sprint |
| 4 | Task Completion Rate | Tasks done / Tasks planned | >= 90% per week | Weekly |
| 5 | System Uptime (Post-deploy) | Server monitoring logs | >= 99% | Daily |
| 6 | User Satisfaction Score (UAT) | Feedback forms | >= 4/5 rating | Post-UAT |

## 6.2 Monitoring Frequency & Reporting Plan

| Report Type | Frequency | Content | Prepared By | Audience |
| --- | --- | --- | --- | --- |
| Weekly Status Report | Every Monday | Task completion, blockers, upcoming tasks | Amir (PM) | Client / Self |
| Milestone Report | Per milestone | Milestone deliverables, status, variance | Amir (PM) | Client |
| Budget Tracking Report | Bi-weekly | Spending vs budget, forecast | Amir (PM) | Client / Self |
| Risk Status Report | Monthly | Active risks, new risks, mitigation update | Amir (PM) | Client |
| Final Completion Report | End of project | Full project summary, lessons learned | Amir (PM) | Client + Records |

## 6.3 Control Mechanisms

- Earned Value Management (EVM) will be used to track Schedule Variance (SV) and Cost Variance (CV) at each milestone.

- Any task delayed by more than 2 days triggers an immediate corrective action plan.

- GitHub commit history will serve as proof of daily progress and code version control.

- All issues and bugs will be logged in GitHub Issues with severity ratings (Critical/High/Medium/Low).

- A dashboard summary will be maintained in a shared Excel tracker updated every Monday.

# 7. Change Management Planning

## 7.1 Change Management Process

- Step 1: Requestor submits a completed Change Request (CR) Form with full description of the proposed change.

- Step 2: Project Manager (Amir) reviews the request and performs an impact analysis on scope, schedule, and cost.

- Step 3: Minor changes (< 1 week delay, < PKR 5,000 cost impact) — approved by Project Manager.

- Step 4: Major changes — escalated to client (Co-Working Space Owner) for formal approval.

- Step 5: Approved changes are documented, project plan updated, and all stakeholders notified.

- Step 6: Rejected changes are documented with reasons and communicated to the requestor.

## 7.2 Impact Assessment Thresholds

| Change Level | Schedule Impact | Cost Impact | Approval Authority |
| --- | --- | --- | --- |
| Minor | Less than 1 week delay | Less than PKR 5,000 | Project Manager (Amir) |
| Moderate | 1–2 weeks delay | PKR 5,000 – 20,000 | Client (Co-Working Owner) |
| Major | More than 2 weeks delay | More than PKR 20,000 | Client + Formal Meeting |

## 7.3 Change Request Form Template

| Field | Details |
| --- | --- |
| CR Reference Number | CR-____ |
| Date of Request |  |
| Requested By |  |
| Change Description |  |
| Reason for Change |  |
| Impact on Scope | [ ] None [ ] Minor [ ] Major |
| Impact on Schedule | Additional time required: ___ days |
| Impact on Cost | Additional cost: PKR ___ |
| Priority | [ ] High [ ] Medium [ ] Low |
| PM Decision | [ ] Approved [ ] Rejected [ ] Deferred [ ] Escalated |
| Approval Signature | Name: _______________ Date: _______________ |

# 8. Rollout Planning

## 8.1 Deployment Strategy

The system follows a phased deployment strategy to minimise risk and ensure smooth transition from development to production.

| # | Phase | Timeline | Activities |
| --- | --- | --- | --- |
| 1 | Development Environment Testing | 03 Mar – 30 Mar 2025 | Unit testing, integration testing, API testing on local/dev server |
| 2 | Staging Environment (UAT) | 31 Mar – 13 Apr 2025 | Deploy to staging server; conduct UAT with real users; collect structured feedback |
| 3 | Production Deployment | 14–20 Apr 2025 | Deploy to live AWS server; configure domain, SSL, monitoring tools |
| 4 | Post-Deployment Monitoring | 21 Apr 2025+ | Monitor uptime, fix bugs, gather user feedback for continuous improvement |

## 8.2 Production Readiness Checklist

| Readiness Item | Status | Notes |
| --- | --- | --- |
| Cloud server (AWS EC2) provisioned | Planned | 2 vCPU, 4GB RAM |
| Domain registered and DNS configured | Planned | Week 14 |
| SSL certificate installed (HTTPS) | Planned | All traffic encrypted |
| Database backup strategy configured | Planned | Daily AWS S3 backups |
| Payment gateway in live mode tested | Planned | Stripe live keys |
| Environment variables & secrets secured | Planned | .env + AWS Secrets Manager |
| Performance & load testing completed | Planned | 50 concurrent users |
| Monitoring & alerting configured | Planned | AWS CloudWatch |

## 8.3 User Training Plan

| Session | Audience | Duration | Format | Topics Covered |
| --- | --- | --- | --- | --- |
| Admin System Training | Space Owner & System Admin | 2 hours | In-person | Dashboard, user management, reports, settings |
| Receptionist Training | Front Desk Staff | 1 hour | In-person | Walk-in bookings, member check-in, queries |
| Client / Member Orientation | Members & Walk-in Clients | 30 min | Video/PDF | Registration, booking, payment, profile management |

## 8.4 Acceptance Criteria

- All functional modules (booking, payment, admin dashboard) working as specified in requirements.

- System passes 100% of defined test cases with no critical defects outstanding.

- UAT sign-off obtained from the co-working space owner.

- System achieves response time of less than 3 seconds for all core transactions.

- User manual and technical documentation delivered and accepted by the client.

- Staff training sessions completed with satisfactory feedback (>= 4/5 rating).

- All data is secure: HTTPS, JWT authentication, and input validation active.

- System deployed on production server with 99%+ uptime in first 72 hours.